### October 2022 EAGLE Uganda Activity Report

### línea horizontal

1. **INTRODUCTION**

This report reflects the period from 1st to 31st October,2022. Project activities are centralized with in the CBD (Central Business District), Kampala with a few extended missions to nearby Districts like Mukono, Entebbe and Wakiso. Performance remains below average as the project continues to build a new team with focus on accomplishing the projects goals.

**INVESTIGATIONS**

The projects major challenge is still in getting the right persons for investigations..

The project continued with 2 investigators in October after 1 opting out.

One candidate had their contract terminated for non-performance.

A few interviews were conducted with most candidates not meeting the project’s expectations.

Field investigations have however been on-going in the different parts of Kampala with small samples of pangolin scales and skins shared.

|  |  |  |
| --- | --- | --- |
| **INVESTIGATION INDICATORS** | | |
| **# of investigations** | **# of investigations that lead to operations** |  |
| **37** | **0** |  |

1. **OPERATIONS**

No operations

|  |  |  |  |
| --- | --- | --- | --- |
| **OPERATION INDICATORS** | | | |
| **# of operations** | **# of operations that lead to arrests** | **# suspect traffickers arrested** | **Contraband (specify units)** |
| **0** | **0** | **0** | **0** |

1. **LEGAL**

The project had 1 candidate on the legal advisory role whose volunteer contract was terminated 2 weeks into October 2022. The Legal candidate participated in the hotel searches and compilation of 3 docs during the 2 weeks before termination.

Among the legal interviews conducted, 1 candidate for the legal advisory role passed the interviews and awaits to start his test period.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **LEGAL INDICATORS** | | | | | |
| **# of court prosecutions** | | **Maximum sentence given** | **# of cases followed** | **# hearings visited** | **# jail visits** |
| **Court of first instance** | **Appeal court** |
| **0** | **0** | **0** | **0** | **0** | **0** |

1. **MEDIA**

Department not operational.

**6.MANAGEMENT**

|  |  |
| --- | --- |
| **MANAGEMENT INDICATORS** | |
| **# investigators on test** | **2** |
| **# legal advisors on test** | **1** |
| **# advocates on test** | **0** |
| **# media journalists on test** | **0** |
| **# accountants on test** | **0** |
| **# internal trainings** | **0** |
| **# external trainings** | **0** |

Several activities carried out by the Ass coordinator were geared towards building and growth of the Uganda team which was the major task at hand,

The activities herein were running throughout the month of October 2022,

* Conducted strategic meeting with the team with continuous evaluations to aid decision making.
* The Ass, Coordinator participated in the compilation of the 3 docs exercise which prepares the team ahead of any operations under the supervision of the Nicolas.
* The need to grow the team fuelled continuous interviews with most candidates not matching the project expectations, meetings with 4 potential recommenders were conducted and its from such meetings that candidates were obtained.
* The Assistant coordinator followed up on the MoU with UAW with Ali (contact person in respect to the MoU) which has been pending for long, follow-up will continue through November.
* All project September reports were duly submitted within the required deadlines to include the Financial & donor report, Activity Report, ICS Legal and Investigation.
* The project’s 2021 books of accounts were audited by external auditors from Morocco and a report to be submitted to the Directors. This was the very first of its kind since the project’s inauguration in 2018.
* November budget request was submitted in time.
* A team family was held with all candidates on test as a social event to bond with one another on 01st October 2022.
* Several activities to foster improvement were conducted (evaluations, simulations, brief meetings) with a focus on reporting lines and format, follow-up & control on targets, EAGLE model for team members, strategy etc.
* Online filing for payment of both PAYE & NSSF for the month of September was done on time.
* Correspondences continued with CCU

1. **EXTERNAL RELATIONS**

|  |  |
| --- | --- |
| **EXTERNAL RELATIONS INDICATORS** | |
| **# of external meetings** | 0 |
| **# of requests for collaboration or support** | 0 |
| **# follow-up meetings related to ongoing agreements/ collaborations** | 0 |
| **# meetings to renew agreements/ collaborations** | 0 |
| **# EAGLE trainings requested from external parties** | 0 |
| **# EAGLE trainings carried out for external parties** | 0 |
| **# EAGLE presentations requested from external parties** | 0 |
| **# EAGLE presentations carried out for others** | 0 |